## Request (hidden)
CHANGE REQUEST |  |  | Data Registered |  | CHANGE REQUEST |  | Data Registered
| ENG | RUS
Change Requst Organizator |  |  |  |  | Change Requst Organizator
Organizator's Organization |  |  |  |  | Organizator's Organization
Category of Change |  |  |  |  | Category of Change
Initiating event |  |  |  |  | Initiating event
Code | ENG | RUS | Date |  | Code |  | Date
Scope of change |  |  |  |  | Scope of change
Document (Code/Name) | Cange description |  | Current rev/ Doc. Status | Organization Developer | Document (Code/Name) | Cange description | Current rev/ Doc. Status | Organization Developer
| ENG | RUS
Agreed |  |  |  |  | Agreed
|  |  |  | Responsible for change management |  |  |  | Responsible for change management

## Order (hidden)
CHANGE ORDER |  |  | Date Registered |  | CHANGE ORDER |  | Date Registered
| ENG | RUS
Creator |  |  |  |  | Creator
CO creator's organization |  |  |  |  | CO creator's organization
Category of Change |  |  |  |  | Category of Change
Initiating event |  |  |  |  | Initiating event
Code | Date of approval | Approved | CR initiator |  | Code | Date of approval | CR initiator
Scope of change |  |  |  |  | Scope of change
Document (Code/Name) | Cange description |  | Responsible | Date of implementation | Document (Code/Name) | Cange description | Responsible | Date of implementation
| ENG | RUS
Agreed |  |  |  |  | Agreed
|  |  |  | Responsible for change management |  |  |  | Responsible for change management

## FCR
FIELD CHANGE REQUEST (FCR)
Field Change Request No: |  | FCR.D-0085/25 |  | Registration date: |  | 2025-01-23 |  | Contractor’s Change Coordinator: |  |  | Leonova Anastasiia
CHANGE INITIATION FORM
Change Initiator's organization: |  | JSC OES Branch in Hungary |  | Change Initiator's internal FCR code: |  | FCR.D-0015/25 |  | Change Initiator: | Ivanilov Aleksander |  | Position of the Change Initiator: |  | Director of JSC OES Branch in Hungary
Type of documentation to be changed: |  |  | DDD |  | Type of changes: | Documentation Red Change |  |  | Type of activity: | Construction |  | Construction facility: |  | CEB
Initiator's proposal for choosing a approval method: |  |  | Normal |  |  | Justification of the 'simple' approval method (Appendix 5 in Procedure):
Change in Project Position of equipment: |  |  | No | Code of reason of engineering change (Appendix 1 to the Procedure): |  |  |  | 4.2 | Other reason:
Description of Engineering Change
Changing the rails, widening the railroad and materials of the dead-end stop for 6.3(UXD)
List of affected SSC
Building/Structure KKS code |  |  |  | System KKS code | [5 empty] | Component KKS code
6.3
UXD
If the code of the SSC is not specified, "N/A" is indicated in the appropriate cell
List of the relevant documents
List of documents from the Documents Set to which it is proposed to change
Document Set Code |  | Set Revision_ version | Engineering Document Code |  | Engineering Document Name |  |  | ED Revision_ version | Sheets or Page numbers | Change (AMx) | Change description (if necessary)
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.SD.0001.H |  | Specification of equipment, items and materials |  |  | C06 | 1,3-5,16-20 | AM1
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0001.H |  | Acél szerelvények összeszerelési és raktározási területe alaprajza (M 1:200). Hossz-szelvény 1-1 (geológiai) (М 1:200). |  |  | C03 | 1 | AM1
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0002.H |  | Metszetek 2-2, 3-3 (M 1:50).Terület vasalásának részlete (М 1:50). Cu1 ... Cu6 csomópontok (M 1:10). |  |  | C03 | 1 | AM1
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0004.H |  | Ütköző UT1 (М1:10) |  |  | C02 | 1 | AM1
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0005.H |  | Lekapcsoló sín berendezés csomópontja (М 1:10) |  |  | C02 | 1 | AM1
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0007.H |  | Sínpálya szerkezete (M 1:50) Cu5, Cu6 (М 1:5) |  |  | C03 | 1 | AM1
CEBP.D.P001.8.0UXD&&03&&&&.012.DC.0001.H |  | C06 | CEBP.D.P001.8.0UXD&&03&&&&.012.BG.0001.H |  | Mennyiségi kimutatás |  |  | C06 | 2,7-8 | AM1
Supporting and describing documents If the document is attached, it should be noted in the field
Filename & extension (if necessary) |  |  | Code, title or summary of the document
CEBP.D.P001.8.0UXD&&03&&&&.012.SD.0001.H_C06_АМ1.pdf |  |  | Specification of equipment, items and materials_pdf format
CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0001.H_C03_AM1.pdf |  |  | Acél szerelvények összeszerelési és raktározási területe alaprajza (M 1:200). Hossz-szelvény 1-1 (geológiai) (М 1:200)._pdf format
CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0002.H_C03_АМ1.pdf |  |  | Metszetek 2-2, 3-3 (M 1:50).Terület vasalásának részlete (М 1:50). Cu1 ... Cu6 csomópontok (M 1:10)._pdf format
CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0004.H_C02_АМ1.pdf |  |  | Ütköző UT1 (М1:10)_pdf format
CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0005.H_C02_AM1.pdf |  |  | Lekapcsoló sín berendezés csomópontja (М 1:10)_pdf format
CEBP.D.P001.8.0UXD&&03&&&&.012.DZ.0006.H_C03_AM1.pdf |  |  | Sínpálya szerkezete (M 1:50) Cu5, Cu6 (М 1:5)_pdf format
CEBP.D.P001.8.0UXD&&03&&&&.012.BG.0001.H_C06_AM1.pdf |  |  | Mennyiségi kimutatás_pdf format
№ CMR 04021276 |  |  | Invoice №04021276
5.1 Datasheet_Crane-tracksleeper-concrete |  |  | crane-track sleeper
2025-01-14
[10 empty] | Initiator's signature* |  |  | dd.mm.yyyy
END OF CHANGE INITIATION FORM
EVALUATION OF A CHANGE REQUEST
For the 'Replacing Of Materials' type of change
The material is equivalent: | [9 empty] | Replace the Type of change with 'Documentation Red Change':
Comments and/or reasons to reject approving replacement of material
Link to documents justifying the decision
Filename & extension (if necessary) |  |  | Code, title or summary of the document
For the 'Documentation Red Change' type of change
Critical Impact | [8 empty] | Non-critical impact |  | Other evaluation results
Nuclear Safety: | No | Fire Safety: | No | Industrial Safety: | No | Environmental safety: |  | No | Schedule: | No | Prompt release of a new revision of the DDD/MDD is required: |  |  | No
Structural reliability and Geometry: |  | No | Impact on other DDD/MDD: |  | No | Licensing Documentation: |  | No | Cost: | No |  |  |  | No
Comments and/or reasons for refusal to approve changes to the documentation
Link to documents justifying the decision
Filename & extension (if necessary) |  |  | Code, title or summary of the document
CONCURRENCE SHEET
Final approval method: |  | Normal |  |  | Justification:
Project Participant position | [5 empty] | Responsible person name |  |  |  | Date |  | Signature*
Responsible person of the Main Participant | [5 empty] | Sniet Pavel |  |  |  | 2025-01-14
Responsible person of the Main Participant
General Designer's responsible person for ChM**
Contractor's Technical Manager, FMV number if relevant*** (Supervisor)
Contractor's ChM Manager
Owner's Supervisor****
Responsible head of the Owner's technical department****
* digital signature can be used for signing the FCR ** If necessary according to the Procedure | [6 empty] | *** As defined in EPC. Not relevant in case of changes in MDD. **** If the 'simple' approval method is selected, the FCR is not approved and signed by the Owner
CLOSE OF CHANGE REQUEST
FCR final status: |  |  |  | Withdrawn / Approved / Approved and the new revision of the DDD/MDD has been developed and agreed upon
END OF CHANGE REQUEST FORM