## Лист1
Change Request No: / Запрос на изменение №: |  |  | CR.D-0007/24 |  |  | Contractor Change Coordinator: / Координатор изменений Подрядчика: |  | Pankov Egor
1.1 General Information (The origin of the Engineering Change)/ Общая информация (Первопричина Инженерного изменения)
Initiator's internal CR No: / Внутренний код Инициатора ЗИ: |  |  | N/A |  |  | Initiator's organization: / Организация инициатора: |  | Atomenergoproekt JSC
Change Initiator: / Инициатор изменения: |  |  | Head of firefighting project team, Sergei Kazakov |  |  | The presence of an impact on documents that need to be revised: / Наличие влияния на документы, которые нужно перевыпускать: |  | No | Type of documentation, where Engineering Change will be reflected : / Тип документации, где будет отражено Инженерное изменение: |  |  |  | CLA/DD
Reason of Engineering Change: / Причина Инженерного изменения: |  |  | Descreasing SGD seismic class in 91UQZ, 92UQZ, 90ULZ, 50UQZ, 60UQZ buildings to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs and these changes don't affect the nuclear safety of the NPP in case DBE (in accordance with Protocol of meeting between the Owner and the Contractor MOM-231201-PAKSII-P2NP-TOM-BOP-02671 dated 01.12.2023)
Initiator's description of technical solution for the Engineering Change: / Описание инициатором технического решения по Инженерному изменению: |  |  | Changing the seismic class to FBOS 4OBE for buildings 91UQZ, 92UQZ, 90ULZ, 50UQZ, 60UQZ
1.2 Supporting and describing documents / Поддерживающие и обосновывающие документы
Filename & extension (if necessary) / Имя файла и расширение (при необходимости) |  |  | Code, title or summary of the document / Код, реквизиты или описание документа
2.1 Impact on the Initiator's TDD / Влияние на TDD Инициатора
TDD code/ Код TDD |  |  | Revision_ Version/ Ревизия_ Версия | Is new revision required?/ Требуется ли новая ревизия? | TDD name/ Название TDD | TDD state/ Статус TDD | Engineering Change description in the TDD/ Описание Инженерного изменения в TDD |  | Potential impact on/ Потенциальное влияния на
[9 empty] | Nuclear safety/ Ядерная безопасность | Fire safety / Пожарная безопасность | Industrial safety / Пром. безопасность | Environmental/ Влияние на окружающую среду | Structural reliability and geometry / Конструктивная надежность и геометрия
PKS2.B.P000.5.&&&&&&SGD&&&.000.SJ.0001.E |  |  | B02 | No | Design Specification. System of automatic water fire-fighting units for main buildings and structures (50SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.04020538&&&&.010.CK.0001.E |  |  | B03 | No | Cable tunnel from 50UQA building to 91UQZ tunnel (50UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.0402053801&&.010.CA.0001.E |  |  | B04 | No | Description (50UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.0402053802&&.010.DP.0001.E |  |  | B03 | No | Drawings (50UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.0938&&&&&&&&.066.CK.0001.E |  |  | B02 | No | Measures for fire safety assurance. Cable tunnel from 50UQA building to 91UQZ tunnel (50UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.093801&&&&&&.066.CA.0001.E |  |  | B02 | No | Technical description of the plant is in accordance with the Recommendation of the Hungarian Chamber of Engineers as regards the general construction part | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.093803&&&&&&.011.DP.0001.E |  |  | B02 | No | Architectural drawings with division into compartments and designation of evacuation routes | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.093806&&&&&&.067.CK.0001.E |  |  | B01 | No | Fire-fighting systems | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.09380602&&&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for main buildings and structures (SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.0938060201&&.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.0938060202&&.067.SD.0001.E |  |  | B02 | No | Specification (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.0938060203&&.067.DP.0001.E |  |  | B02 | No | Drawings (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.9A0602&&&&&&.067.HE.0001.E |  |  | B06 | No | System of Automatic Water Fire-Fighting Units for Main Buildings and Structures (SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.9B0234&&&&&&.010.HE.0001.E |  |  | B02 | No | Cable Tunnel from 50UQA Building to 91UQZ Tunnel (50UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.9B031903&&&&.010.HE.0001.E |  |  | B03 | No | Cable Tunnel Between 93UYA Building and 91UQZ Tunnel (90ULZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.04020637&&&&.010.CK.0001.E |  |  | B03 | No | Cable tunnel from 60UQA building to 92UQZ tunnel (60UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.0402063701&&.010.CA.0001.E |  |  | B04 | No | Description (60UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.0402063702&&.010.DP.0001.E |  |  | B03 | No | Drawings (60UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.0973&&&&&&&&.066.CK.0001.E |  |  | B02 | No | Measures for fire safety assurance. Cable tunnel from 60UQA building to 92UQZ tunnel (60UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.097301&&&&&&.066.CA.0001.E |  |  | B02 | No | Technical description of the plant is in accordance with the Recommendation of the Hungarian Chamber of Engineers as regards the general construction part | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.097303&&&&&&.011.DP.0001.E |  |  | B02 | No | Architectural drawings with division into compartments and designation of evacuation routes | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.097306&&&&&&.067.CK.0001.E |  |  | B01 | No | Fire-fighting systems | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.09730602&&&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for main buildings and structures (SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.0973060201&&.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.0973060202&&.067.SD.0001.E |  |  | B02 | No | Specification (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.6.0973060203&&.067.DP.0001.E |  |  | B02 | No | Drawings (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.04020754&&&&.010.CK.0001.E |  |  | B03 | No | Cable tunnel between 93UYA building and 91UQZ tunnel (90ULZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.0402075401&&.010.CA.0001.E |  |  | B04 | No | Description (90ULZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.0402075402&&.010.DP.0001.E |  |  | B03 | No | Drawings (90ULZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.04020755&&&&.010.CK.0001.E |  |  | B03 | No | Cable tunnel from 90UBV building to 90UXR building (91UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.0402075501&&.010.CA.0001.E |  |  | B04 | No | Description (91UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.0402075502&&.010.DP.0001.E |  |  | B03 | No | Drawings (91UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.04020756&&&&.010.CK.0001.E |  |  | B03 | No | Cable tunnel from 90UBV building to 90UTF building (92UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.0402075601&&.010.CA.0001.E |  |  | B04 | No | Description (92UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.0402075602&&.010.DP.0001.E |  |  | B03 | No | Drawings (92UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&&&&&&&.066.CK.0001.E |  |  | B03 | No | Measures for fire safety assurance. Cable tunnel between 93UYA building and 91UQZ tunnel(90ULZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&01&&&&.066.CA.0001.E |  |  | B02 | No | Technical description of the plant is in accordance with the Recommendation of the Hungarian Chamber of Engineers as regards the general construction part | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&03&&&&.011.DP.0001.E |  |  | B02 | No | Architectural drawings with division into compartments and designation of evacuation routes | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&06&&&&.067.CK.0001.E |  |  | B01 | No | Fire-fighting systems | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&0602&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for main buildings and structures (SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&060201.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&060202.067.SD.0001.E |  |  | B02 | No | Specification (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&060203.067.DP.0001.E |  |  | B02 | No | Drawings (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09101&060301.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&&&&&&&.066.CK.0001.E |  |  | B03 | No | Measures for fire safety assurance. Cable tunnel from 90UBV building to 90UXR building (91UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&01&&&&.066.CA.0001.E |  |  | B02 | No | Technical description of the plant is in accordance with the Recommendation of the Hungarian Chamber of Engineers as regards the general construction part | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&03&&&&.011.DP.0001.E |  |  | B02 | No | Architectural drawings with division into compartments and designation of evacuation routes | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&06&&&&.067.CK.0001.E |  |  | B01 | No | Fire-fighting systems | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&0603&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for main buildings and structures (SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&060301.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&060302.067.SD.0001.E |  |  | B02 | No | Specification (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&060303.067.DP.0001.E |  |  | B02 | No | Drawings (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&&&&&&&.066.CK.0001.E |  |  | B03 | No | Measures for fire safety assurance. Cable tunnel from 90UBV building to 90UTF building (92UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&01&&&&.066.CA.0001.E |  |  | B02 | No | Technical description of the plant is in accordance with the Recommendation of the Hungarian Chamber of Engineers as regards the general construction part | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&03&&&&.011.DP.0001.E |  |  | B02 | No | Architectural drawings with division into compartments and designation of evacuation routes | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&06&&&&.067.CK.0001.E |  |  | B01 | No | Fire-fighting systems | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&0603&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for main buildings and structures (SGD) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&060301.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&060302.067.SD.0001.E |  |  | B02 | No | Specification (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&060303.067.DP.0001.E |  |  | B02 | No | Drawings (System of automatic water fire-fighting units for main buildings and structures (SGD)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.5.9B0232&&&&&&.010.HE.0001.E |  |  | B02 | No | Cable Tunnels from 90UBV Building (91, 92UQZ) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&0602&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for auxiliary buildings and structures (SGC) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&0602&&.067.CK.0001.E |  |  | B02 | No | System of automatic water fire-fighting units for auxiliary buildings and structures (SGC) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&060201.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&060201.067.CA.0001.E |  |  | B02 | No | Description (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&060202.067.SD.0001.E |  |  | B01 | No | Specification (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&060202.067.SD.0001.E |  |  | B01 | No | Specification (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09102&060203.067.DP.0001.E |  |  | B01 | No | Drawings (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
PKS2.B.P000.9.09103&060203.067.DP.0001.E |  |  | B01 | No | Drawings (System of automatic water fire-fighting units for auxiliary buildings and structures (SGC)) | Approved | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
2.2. Impact on the other TDD / Влияние на другую TDD
Evaluation organization / Организация, проводящая оценку | TDD code/ Код TDD |  | Revision_ Version/ Ревизия_ Версия | Is new revision required?/ Требуется ли новая ревизия? | TDD name/ Название TDD | TDD state/ Статус TDD | Engineering Change description in the TDD/ Описание Инженерного изменения в TDD |  | Potential impact on / Потенциальное влияния на
[9 empty] | Nuclear safety/ Ядерная безопасность | Fire safety / Пожарная безопасность | Industrial safety / Пром. безопасность | Environmental/ Влияние на окружающую среду | Structural reliability and geometry / Конструктивная надежность и геометрия
Atomenergoproekt JSC | PKS2.L.P000.9.1UQZ&&&&&&&&.000.JE.0001.E |  | B01 | No | Design Bases of Buildings and Structures (91UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.9.2UQZ&&&&&&&&.000.JE.0001.E |  | B01 | No | Design Bases of Buildings and Structures (92UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.5.0UQZ&&&&&&&&.000.JE.0001.E |  | B01 | No | Design Bases of Buildings and Structures (50UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.9.1UQZ&&&&&&&&.010.PH.0001.E |  | B01 | No | Design Program (91UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.9.2UQZ&&&&&&&&.010.PH.0001.E |  | B01 | No | Design Program (92UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.9.0ULZ &&&&&&&&.010.PH.0001.E |  | B01 | No | Design Program (90 ULZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.5.0UQZ &&&&&&&&.010.PH.0001.E |  | B01 | No | Design Program (50UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.6. 0UQZ &&&&&&&&.010.PH.0001.E |  | B01 | No | Design Program (60UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.D.P000.&.&&&&&&SGD&&&.021.CB.0001.E |  | B01 | No | Description (System of Automatic Water Fire-Fighting Units for Main Buildings and Structures (SGD)) | Development | Changing the seismic class to FBOS 4OBE |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.D.P000.9.1UQZ&&&&&&&&.012.CB.0002.E |  | B01 | No | Design Basis 91UQZ | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.D.P000.9.2UQZ&&&&&&&&.012.CB.0002.E |  | B01 | No | Design Basis 92UQZ | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.D.P000.9.0ULZ&&&&&&&&.012.CB.0002.E |  | B01 | No | Design Basis 90ULZ | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.D.P000.5.0UQZ&&&&&&&&.012.CB.0002.E |  | B01 | No | Design Basis 50UQZ | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.D.P000.6.0UQZ&&&&&&&&.012.CB.0002.E |  | B01 | No | Design Basis 60UQZ | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.9.0ULZ&&&&&&&&.000.JE.0001.E |  | B01 | No | Design Bases of Buildings and Structures (90ULZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
Atomenergoproekt JSC | PKS2.L.P000.6.0UQZ&&&&&&&&.000.JE.0001.E |  | B01 | No | Design Bases of Buildings and Structures (60UQZ) | Development | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs |  | No | No | No | No | No
2.3. Mail affected SSC / Попавшие под влияние основные КСК
KKS code/ Код KKS | Name of SSC/ Наименование КСК |  |  |  | Engineering Change description/ Описание Инженерного изменения
50UQZ | Cable tunnel from 50UQA building to 91UQZ tunnel / Кабельный тоннель от здания 50UQA до тоннеля 91UQZ |  |  |  | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs
60UQZ | Cable tunnel from 60UQA building to 92UQZ tunnel / Кабельный тоннель от здания 60UQA до тоннеля 92UQZ |  |  |  | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs
90ULZ | Cable tunnel between 93UYA building and 91UQZ tunnel / Кабельный тоннель от здания 93UYA до тоннеля 91UQZ |  |  |  | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs
91UQZ | Cable tunnel from 90UBV building to 90UXR building / Кабельный тоннель от здания 90UBV до здания 90UXR |  |  |  | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs
92UQZ | Cable tunnel from 90UBV building to 90UTF building / Кабельный тоннель от здания 90UBV до здания 90UTF |  |  |  | Changing the seismic class to FBOS 4OBE, because these building don't contain FBOS 1-3 SSCs
50SGD05AA040 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
50SGD08AA031 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
50SGD08AA032 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
50SGD08AA033 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
60SGD05AA035 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
60SGD08AA023 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
60SGD08AA024 | Rotary interflange butterfly valve with counterflanges for butt welding, gaskets, fastener and position indicator / Затвор дисковый поворотный межфланцевый с ответными фланцами под приварку в стык, прокладками, крепежом и датчиком положения |  |  |  | Changing the seismic class to FBOS 4OBE
2.4. Final evaluation results / Конечные результаты оценки
Final NSC category of the Engineering Change: / Конечная категория Инженерного изменения по КЯБ: |  | b/bb | Presence of direct or indirect impact on equipment of 1,2 and 3 safety classes / Наличие прямого или косвенного влияния на оборудования 1,2 и 3 класса безопасности |  |  | No | Presence the impact on the results DSA or Hazard reports for the worse: / Наличие влияния на результаты ДАБ или отчетов об опасностях в худшую сторону: | No | Method* of CR:/ Вид ЗИ: |  |  |  | Normal
Comments for engineering evaluation: / Комментарии к инженерной оценке:
2.5. Non-technical assessment for the Contractor / Нетехническая оценка для Подрядчика
Contract (its presence indicates the need to make changes to the terms of the Contract): / Контракт (его наличие указывает на необходимость внесения изменений в условия Контракта): | [5 empty] | No | Cost impact: / Влияние на стоимость: | No | Schedule: / График: |  |  |  | No
Comments for non-technical assessment: / Комментарии к нетехнической оценке:
3. Confirmation/ Подтверждение
Organization/Организация | Position**/Должность |  |  | Responsible person/ Ответственное лицо |  |  |  | Signature***/ Подпись | Date/ Дата
Atomenergoproekt JSC | Deputy Chief Engineer of the Project |  |  | Berezin Nikolay |  |  |  |  | 09.01.2025
4. Approval/ Согласование
Position/Должность |  |  |  | Responsible person/ Ответственное лицо |  |  |  | Signature***/ Подпись | Date/ Дата
Change Manager of the Contractor |  |  |  | Deputy Director for Licensing and Quality, Obushev A.E. |  |  |  |  | 2025-01-09
Change Manager of the Owner
*if the CR is classified as a Simple, the chapter 4 is blank / Если ЗИ классифицирован как Простой, раздел 4 не заполняется
**if the organization is not connect to Owner IMS, the Contractor Change Coordinator signs the CR/ Если организация не подключена к СУИ Заказчика, Координатор изменений Подрядчика подписывает ЗИ
***digital signature can be used to sign the CR / Электронная цифровая подпись может быть использована для подписи ЗИ