## Лист1
Change Request No: / Запрос на изменение №: |  |  | CR-D-0008/25 |  |  | Contractor Change Coordinator: / Координатор изменений Подрядчика: |  | Pankov Egor
1.1 General Information (The origin of the Engineering Change)/ Общая информация (Первопричина Инженерного изменения)
Initiator's internal CR No: / Внутренний код Инициатора ЗИ: |  |  | N/A |  |  | Initiator's organization: / Организация инициатора: |  | BAUER Magyarország Speciális Mélyépitö Kft.
Change Initiator: / Инициатор изменения: |  |  | Senior Project Director, Mark Ingram |  |  | The presence of an impact on documents that need to be revised: / Наличие влияния на документы, которые нужно перевыпускать: |  | No | Type of documentation, where Engineering Change will be reflected : / Тип документации, где будет отражено Инженерное изменение: |  |  |  | DDD
Reason of Engineering Change: / Причина Инженерного изменения: |  |  | Changes in soil improvement levels, partial cancellation of soil improvement under buildings. Redistribution of SI between package 1, 2 and 3.
Initiator's description of technical solution for the Engineering Change: / Описание инициатором технического решения по Инженерному изменению: |  |  | Changed SI Layout; Changed Key plan; Changed coordinates of 2 inclinometers by analogy of Unit 6; Added docement PKS2.D.H004.&.020001&&&&&&.000.DZ.0013.E; Additional scope in packages 1, 2 & 3; Removed scope from packages 1, 2 & 3; Lower SI levels in unit 6; Lower GEWI levels in unit 6; Extended SI under the secant wall in unit 6; Proposal leak sealing to the SI & secant wall after excavation; Add option to use empty drilling material as protective measures for the improved soil and to use geotextile as a protective material against falling of the empty drilling parts into the pit; Add option to use bentonite as an additive in the production of DSM columns; Design details of completion works to rectify identified gaps; Updated Organization and Traffic Management plan; Changes stages for the production of 3 soil reinforcement packages; technical solution of Unit 5 inner pit corner for the construction 50USG building; Technical solution for shotcrete and soil nails.
1.2 Supporting and describing documents / Поддерживающие и обосновывающие документы
Filename & extension (if necessary) / Имя файла и расширение (при необходимости) |  |  | Code, title or summary of the document / Код, реквизиты или описание документа
CR.D-0008-25_rev2.rar
2.1 Impact on the Initiator's TDD / Влияние на TDD Инициатора
TDD code/ Код TDD |  |  | Revision_ Version/ Ревизия_ Версия | Is new revision required?/ Требуется ли новая ревизия? | TDD name/ Название TDD | TDD state/ Статус TDD | Engineering Change description in the TDD/ Описание Инженерного изменения в TDD |  | Potential impact on/ Потенциальное влияния на
[9 empty] | Nuclear safety/ Ядерная безопасность | Fire safety / Пожарная безопасность | Industrial safety / Пром. безопасность | Environmental/ Влияние на окружающую среду | Structural reliability and geometry / Конструктивная надежность и геометрия
2.2. Impact on the other TDD / Влияние на другую TDD
Evaluation organization / Организация, проводящая оценку | TDD code/ Код TDD |  | Revision_ Version/ Ревизия_ Версия | Is new revision required?/ Требуется ли новая ревизия? | TDD name/ Название TDD | TDD state/ Статус TDD | Engineering Change description in the TDD/ Описание Инженерного изменения в TDD |  | Potential impact on / Потенциальное влияния на
[9 empty] | Nuclear safety/ Ядерная безопасность | Fire safety / Пожарная безопасность | Industrial safety / Пром. безопасность | Environmental/ Влияние на окружающую среду | Structural reliability and geometry / Конструктивная надежность и геометрия
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.CK.0001.E |  | C12 | Yes | Title page | Approved | Changed SI Layout; Changed Key plan; Changed coordinates of 2 inclinometers by analogy of Unit 6; Added docement PKS2.D.H004.&.020001&&&&&&.000.DZ.0013.E; Additional scope in packages 1, 2 & 3; Removed scope from packages 1, 2 & 3; Lower SI levels in unit 6; Lower GEWI levels in unit 6; Extended SI under the secant wall in unit 6; Proposal leak sealing to the SI & secant wall after excavation; Add option to use empty drilling material as protective measures for the improved soil and to use geotextile as a protective material against falling of the empty drilling parts into the pit; Add option to use bentonite as an additive in the production of DSM columns; Design details of completion works to rectify identified gaps; Updated Organization and Traffic Management plan; Changes stages for the production of 3 soil reinforcement packages; technical solution of Unit 5 inner pit corner for the construction 50USG building; Technical solution for shotcrete and soil nails. |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.HG.0001.E |  | C11 | Yes | Technical report | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.HG.0003.E |  | C04 | Yes | Geotechnical and structural calculations | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0001.E |  | C04 | Yes | General data sheet | Approved | Changed SI Layout; Changed Key plan; Changed coordinates of 2 inclinometers by analogy of Unit 6; Added docement PKS2.D.H004.&.020001&&&&&&.000.DZ.0013.E; Additional scope in packages 1, 2 & 3; Removed scope from packages 1, 2 & 3; Lower SI levels in unit 6; Lower GEWI levels in unit 6; Extended SI under the secant wall in unit 6; Proposal leak sealing to the SI & secant wall after excavation; Add option to use empty drilling material as protective measures for the improved soil and to use geotextile as a protective material against falling of the empty drilling parts into the pit; Add option to use bentonite as an additive in the production of DSM columns; Design details of completion works to rectify identified gaps; Updated Organization and Traffic Management plan; Changes stages for the production of 3 soil reinforcement packages; technical solution of Unit 5 inner pit corner for the construction 50USG building; Technical solution for shotcrete and soil nails. |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0002.E |  | C04 | Yes | General layout | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0003.E |  | C04 | Yes | Geodetic survey plan | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0004.E |  | C05 | Yes | Soil improvement for NI Unit 5 and surrounding buildings | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0005.E |  | C04 | Yes | Soil improvement for NI Units 5 and 6 and surrounding buildings on geological sections | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.HG.0005.E |  | C02 | Yes | Detailed design documentation for assessment of impacts of soil improvement execution for Paks II NPP on Paks NPP site | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0006.E |  | C07 | Yes | Secant pile wall for NI Unit 5 | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.089.QD.0001.E |  | C06 | Yes | Quality plan | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.089.QC.0001.E |  | C07 | Yes | Quality control plan | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0007.E |  | C05 | Yes | GEWI piles of Unit 5 | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0008.E |  | C03 | Yes | Soil improvement for NI Unit 6 and surrounding buildings | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0009.E |  | C05 | Yes | Secant pile wall for NI Unit 6 | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0010.E |  | C04 | Yes | GEWI piles of Unit 6 | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0011.E |  | C03 | Yes | Soil improvement for other buildings on site | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0012.E |  | C01 | Yes | Injection tubes in area of DSM pockets and cut-off wall adjunction | Approved | Changed SI Layout; Changed Key plan; Changed coordinates of 2 inclinometers by analogy of Unit 6; Added docement PKS2.D.H004.&.020001&&&&&&.000.DZ.0013.E; Additional scope in packages 1, 2 & 3; Removed scope from packages 1, 2 & 3; Lower SI levels in unit 6; Lower GEWI levels in unit 6; Extended SI under the secant wall in unit 6; Proposal leak sealing to the SI & secant wall after excavation; Add option to use empty drilling material as protective measures for the improved soil and to use geotextile as a protective material against falling of the empty drilling parts into the pit; Add option to use bentonite as an additive in the production of DSM columns; Design details of completion works to rectify identified gaps; Updated Organization and Traffic Management plan; Changes stages for the production of 3 soil reinforcement packages; technical solution of Unit 5 inner pit corner for the construction 50USG building; Technical solution for shotcrete and soil nails. |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.HG.0002.E |  | C10 | Yes | Construction organization plan | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.DZ.0018.E |  | C09 | Yes | Organizational Plan | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.000.YP.0001.E |  | C02 | Yes | Time schedule | Approved |  |  | No | No | No | No | No
JSC ASE | PKS2.D.H004.&.020001&&&&&&.089.DZ.0001.E |  | C07 | Yes | Health Safety and Environmental Plan - Traffic Management Plan | Approved |  |  | No | No | No | No | No
2.3. Mail affected SSC / Попавшие под влияние основные КСК
KKS code/ Код KKS | Name of SSC/ Наименование КСК |  |  |  | Engineering Change description/ Описание Инженерного изменения
N/A | N/A |  |  |  | N/A
2.4. Final evaluation results / Конечные результаты оценки
Final NSC category of the Engineering Change: / Конечная категория Инженерного изменения по КЯБ: |  | b/bb | Presence of direct or indirect impact on equipment of 1,2 and 3 safety classes / Наличие прямого или косвенного влияния на оборудования 1,2 и 3 класса безопасности |  |  | No | Presence the impact on the results DSA or Hazard reports for the worse: / Наличие влияния на результаты ДАБ или отчетов об опасностях в худшую сторону: | No | Method* of CR:/ Вид ЗИ: |  |  |  | Complex
Comments for engineering evaluation: / Комментарии к инженерной оценке:
2.5. Non-technical assessment for the Contractor / Нетехническая оценка для Подрядчика
Contract (its presence indicates the need to make changes to the terms of the Contract): / Контракт (его наличие указывает на необходимость внесения изменений в условия Контракта): | [5 empty] | No | Cost impact: / Влияние на стоимость: | No | Schedule: / График: |  |  |  | No
Comments for non-technical assessment: / Комментарии к нетехнической оценке:
3. Confirmation/ Подтверждение
Organization/Организация | Position**/Должность |  |  | Responsible person/ Ответственное лицо |  |  |  | Signature***/ Подпись | Date/ Дата
Atomenergoproekt JSC | Deputy Director for Design of Paks-2 NPP |  |  | Kabanov V.E. |  |  |  |  | 26.02.2025
JSC ASE | Chief Expert |  |  | Feher Imre |  |  |  |  | 26.02.2025
4. Approval/ Согласование
Position/Должность |  |  |  | Responsible person/ Ответственное лицо |  |  |  | Signature***/ Подпись | Date/ Дата
Change Manager of the Contractor |  |  |  | Chief Engineer JSC ASE branch in Hungary, Pushkarev S.V. |  |  |  |  | 26.02.2025
Change Manager of the Owner
*if the CR is classified as a Simple, the chapter 4 is blank / Если ЗИ классифицирован как Простой, раздел 4 не заполняется
**if the organization is not connect to Owner IMS, the Contractor Change Coordinator signs the CR/ Если организация не подключена к СУИ Заказчика, Координатор изменений Подрядчика подписывает ЗИ
***digital signature can be used to sign the CR / Электронная цифровая подпись может быть использована для подписи ЗИ